## SPRINT BACKLOG
SPRINT REFINE BACKLOG
ID | User Story | Tasks | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US001 | As a user I can check all the resturants discout offers near by me and can check all shops | Install google maps | Completed | 60 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add all discount new offers | Completed |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete custom configuration as agreed in project management plan. | Completed |  | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | As a user, I can avail every type of discount offer through shops on my order and add to cart .. | Install add cart widget on portal | Completed | 48 | 0 | 0 | 5 | 7 | 2 | 8 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Apply customer offers | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
US003 | As a a user I can add or delete any offer and can take any package of shop | Install offers page. | Completed | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  | Integrate postcode plugin to contact page. | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0
|  | Install packages to contact page of shops, | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
|  | Complete any changes required from user. | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  |  | 132 | 0.5 | 8 | 11 | 9 | 2 | 8 | 6 | 6 | 7 | 3 | 2 | 8 | 6 | 4 | 8

## PROJECT DETAILS
PROJECT NUMBER | 1
PROJECT NAME | Digital Discount App
PROJECT MANAGER | PM
DATE | 2022-11-03
VERSION | 1